VOTER CHOICE ACT ELECTION ADMINISTRATION PLAN

TIMELINE

July 17, 2017 Solicitation to local entities and County Agencies to identify potential Voter Accessibility Advisory Committee (VAAC) and Language Access Advisory Committee (LAAC) members. Includes media and social media releases inviting participation COMPLETED

July 17 – August 22, 2017 Compilation of prospective VAAC and LAAC members IN PROGRESS\*

August 3, 2017 Combined meeting of possible VAAC and LAAC members to discuss next steps in process and review materials for distribution. COMPLETED

August 11, 2017 Public notification regarding public comment on tentative Election Administration Plan (EAP) COMPLETED

August 21, 2017 Public consultation for voters with disabilities and support groups – American Canyon Library 7-8 p.m. COMPLETED

August 22, 2017 Public consultation for language minority community - and voters with disabilities to aid in the development of a draft EAP (date and time to be determined after August 3 meeting) COMPLETED

September 12, 2017 Board opportunity for input on Draft EAP/outreach

October 2, 2017\*\* EAP Public hearing conducted by Registrar Of Voters 10:00 a.m. Napa County Board of Supervisors Chambers 1195 3rd Street Napa CA 3rd Floor

October 16, 2017 ROV review comments and adopt EAP and submit Outreach plan to Secretary of State (SOS)

\*LAAC and VAAC initial meetings to be scheduled prior to October 2, 2017.