## Sheet1
IMOLA AVE POCKET PAVING AND ADA RAMP | 2018-12-05
PROJECT, RDS 18-24
CONSTRUCTION PHASE
|  | Board Appropriation | Board Appropriation | Appropriation Amount | Appropriation Amount | Appropriation Amount
Budget Item | Budget Item Amount | Request Today | to date | Spent to Date | % Spent to Date | Balance
Construction | 1757880 | 289400 | 1468480 | 0 | 0% | 1468480
Construction Contingency (10%) | 175788 | 28940 | 146848 | 0 | 0% | 146848
Design and Engineering |  | 0 | 209585 | 65000 | 31.01% | 144585
Mark Thomas & Co. | 194585 |  | 194585
Michael Baker | 15000 |  | 15000
Design and Engineering Contingency | $17,500* | 0 | 53518 | 0 | 0% | 53518
Construction Management | 83518 | 0 | 83518 | 0 | 0% | 83518
County Project Management/Administration | $66,018* | 0 | 30000 | 42770 | 64.79% | 23248
Inspections and Fees | 15000 | 0 | 15000 | 0 | 0% | 15000
TOTAL | 2325289 | 318340 | 2006949 | 107770 | 5.37% | 1935197
* Staff has moved $36,018 of budgeted funding from Design and Engineering Contingency to County Project Management/Administration to better represent the estimated costs associated with each budget item.