NAPA COUNTY GENERAL PLAN UPDATE

IMPLEMENTATION ACTION ITEMS

(Updated: March 8, 2010)

| Action Items | Action | Timing/Priority & Cost | Responsible Party | Notes & Status |
| --- | --- | --- | --- | --- |
| Agricultural Preservation and Land Use Element |  |  |  |  |
| Action Item AG/LU-2.1 | Amend County Code to reflect the definition of “agriculture” as set forth within this Plan ensuring that wineries and other production facilities remain as conditional uses except as provided for in Policy AG/LU-16, and that marketing activities and other accessory uses remain incidental and subordinate to the main use. | A $ | CDPD | Planned for 2010 |
| Action Item AG/LU-7.1 | Work with interested stakeholders to undertake an evaluation of new voluntary approaches to protecting agriculture, including implementation of a “Super Williamson Act” program, a conservation easement program or other permanent protections, and programs promoting the economic viability of agriculture. | Ongoing $ | CDPD | Ongoing |
| Action Item AG/LU-10.1 | Maintain a data base of all wineries including their production capacity, marketing events and other characteristics that could influence analysis of cumulative effects or the winery’s effect on neighbors. | A $ | CDPD | Database maintained as ongoing part of CDPD work program |
| Action Item AG/LU-15.5.1 | The County will prepare and adopt guidelines and regulations to assist in the determination of the appropriate type and scope of agricultural buffer areas needed in circumstances that warrant the creation of such buffer. | A $$$$ | CDPD | Not yet programmed |
| Action Item AG/LU-16.1 | Consider amendments to the Zoning Ordinance defining “small wineries,” a “small quantity of wine,” “small marketing events,” and “mostly grown on site,” and establishing a streamlined permitting process for small wineries which retains the requirement for a use permit when the winery is in proximity to urban areas. | A $ | CDPD | Not yet programmed |
| Action Item AG/LU-30.1 | Develop a Workforce Housing Ordinance, including revisions to the current Inclusionary Housing Ordinance, to define workforce housing and establish additional workforce and inclusionary housing requirements for all multi-family housing proposals consisting of eight or more units constructed in the unincorporated County. Such an ordinance could also require on-site workforce housing in place of in-lieu fees for any large commercial or institutional projects constructed outside of areas where housing would be inconsistent with the applicable airport land use compatibility plan. | Concurrent with 2008-09 Housing Element Update $$$$ | CDPD CIA | Expected to be completed in 2010 |
| Action Item AG/LU-33.1 | Adopt local guidelines or zoning code definitions to clarify the distinction between single-family residences and commercial short-term guest accommodations, specifying the uses and ownership or rental arrangements associated with each. Also, analyze the prevalence of extremely large residences, and determine whether single family residences above a certain size should require environmental analysis. | A $$ | CDPD | First part addressed by ordinance adopted Dec. 2009; second part not yet programmed. |
| Action Item AG/LU-43.1 | Consider amendments to the Zoning Code to allow additional commercial, residential, and mixed uses in the areas currently zoned for commercial use in the Spanish Flat, Moskowite Corner, and southern Pope Creek areas in order to complement recreation activities at Lake Berryessa. | B $ | CDPD | Planned for 2011 after BOR completes plans/contracts. |
| Action Item AG/LU-45.1 | Review and revise sections of the Napa County Code that provide the list of land uses permitted on existing commercially zoned parcels to encourage neighborhood-serving commercial uses and new limited accessory dwellings where appropriate. | B $ | CDPD | Not yet programmed |
| Action Item AG/LU-48.1 | Review zoning code requirements for Home Occupation permits, and update those requirements to provide greater flexibility in situations where there will be no off-site impacts. For example, consider situations in which the use of legal, accessory structures could be permitted, or where home occupations could employ workers other than a single owner/proprietor. | B $ | CDPD | Not yet programmed |
| Action Item AG/LU-49.1 | Refer General Plan land use changes, proposed rezonings, and proposed developments in Airport Approach Zones to the Napa County Airport Land Use Commission for review and comment. | Ongoing $ | CDPD | Ongoing: This referral is routinely accomplished by staff and required by State law |
| Action Item AG/LU-54.5.1 | Develop a definition of ‘formula businesses’ and amend County Code to ensure compatibility with ordinances related to this issue in Calistoga and St. Helena. | B $ | CDPD | Not yet programmed |
| Action Item AG/LU-94.1 (MM 4.2.1) | Prior to approving non-industrial development, the County shall adopt development standards for the Pacific Coast/Boca and Napa Pipe sites which shall include, but may not be limited to, buffering and visual screening from existing industrial uses and Syar Quarry, design features that include physical buffers (e.g., vegetation, landscape features, or walls in unique circumstances), building placement and orientation in a manner that physically separates these sites from incompatible operations of adjacent uses (e.g., truck traffic, odors, stationary noise sources), and implementation of other measures to address noise and vibration. Standards for the Napa Pipe site shall ensure conformance with the Napa County Airport Land Use Compatibility Plan. | A $ | CDPD | Standards will be developed as part of site specific planning and prior to approval of non-industrial uses on these sites |
| Action Item AG/LU-107.1 | Undertake revisions to the zoning ordinance (County Code Title 18), simplifying and reorganizing to the extent feasible so that members of the public, applicants, planners, and decision makers can more easily access information and understand code requirements. | C $$$ | CDPD | Not yet programmed |
| Action Item AG/LU-114.1 | Undertake a planning effort to re-evaluate areas of Angwin designated Urban Residential after June 2010, with the objective of re-designating areas to better reflect land uses existing or authorized at that time. | A $$$ | CDPD | Ongoing |
| Action Item AG/LU-119.1 | Complete the Review Following Census called for in Section (3) of Policy AG/LU-119 during each update to the Housing Element required by State law. | Concurrent with 2008-09 Housing Element Update $ | CDPD CIA | Completed with Housing Element adoption June 2009. |
| Action Item AG/LU-125.1 | Consider amendments to the Zoning Code that would reduce the number of zoning districts in which new churches and religious institutions may be located and provide siting criteria as part of the use permit process. | B $ | CDPD | Expected to be completed in 2010 |
| Circulation Element |  |  |  |  |
| Action Item CIR-10.1 | County staff shall participate in the periodic updates of the Napa County Transportation and Planning Agency’s Strategic Transportation Plan (STP), and use that forum for consideration and development of innovative strategies related to the movement of people and services without increasing the use of private vehicles. The County shall seek input from experts in sustainability, smart growth, and land use planning in developing potential new strategies. | Ongoing $ | CDPD PW NCTPA | Ongoing as a part of regular planning process; consultation with experts as needed. |
| Action Item CIR-11.1 | The County shall adopt, periodically review, and revise as appropriate specific road and street standards for County roads. These standards shall include overall right-of-way widths, pavement widths, lane and shoulder widths, and other design details. The County’s roadway standards shall be developed in consultation with the County Fire Marshal, County Public Works, and others to ensure adequate widths for safety and emergency access and evacuation. | Ongoing $ | PW CDPD CalFire | The road and street standards were recently reviewed and modified. |
| Action Item CIR-13.1 | Work with the Napa County Transportation and Planning Agency and other agencies to fund and implement the improvements listed in Policy CIR-13. | Ongoing $$$ | PW NCTPA | Ongoing |
| Action Item CIR-16.1 | Work with the Napa County Transportation Authority, adjacent counties, the Metropolitan Transportation Commission, and the California Department of Transportation to monitor traffic volumes and congestion on the roadway system in Napa County. | Ongoing $ | PW NCTPA | Ongoing monitoring and coordination with other agencies |
| Action Item CIR-19.1 (MM 4.4.1c) | In cooperation with the Napa County Transportation and Planning Agency, develop a countywide traffic impact fee to address cumulative (i.e., not project-specific) impacts associated with new employment. Fees shall be used to pay for the cost of network improvements listed in Policy CIR-13 as well as other transportation improvements such as transit. | A $$$$ | PW CDPD NCTPA: Cities of: Am Cyn, Calistoga Napa, St. Helena, and Town of Yountville | Not yet programmed |
| Action Item CIR-22.1 | The County shall work with the incorporated cities and town, the Napa County Transportation and Planning Agency, and Caltrans to develop a coordinated approach to roadway design to enhance driver and pedestrian safety, particularly for children and senior citizens. | Ongoing $ | PW CDPD NCTPA all cities referenced in CIR-2.9.1 | Ongoing |
| .Action Item CIR-26.1 | The County will work with the Napa County Transportation and Planning Agency to conduct regular reviews of public transit use and opportunities for its expansion in Napa County. | Ongoing $ | PW NCTPA | Ongoing |
| Action Item CIR-26.2 | The County shall establish targets for interim years to enable the County to monitor progress towards its objective of reducing the percentage of work trips that are by private, single occupant vehicles to 50%. | Ongoing $ | PW CDPD NCTPA as part of its Strategic Trans. Plan Update | Will be developed as part of the County’s plan for reducing green house gases in 2010 (see Action Item CON CPSP-2). |
| Action Item CIR-28.1 | Work with major employers and the Napa County Transportation and Planning Agency to offer incentives for carpooling and the use of cost-efficient ground transportation alternatives to the private automobile. | A $ | PW NCTPA CIA WIB | Same as Action Item CIR-26.2 above |
| Action Item CIR-28.2 | Adopt hours of operation/schedules for County meetings (e.g., Planning Commission and Board of Supervisors) which are coordinated with public transit availability in order to make it easier for residents to use transit when doing business with the County. The County shall encourage schools and other public agencies to do the same. | Ongoing $ | PW CDPD NCTPA | Ongoing |
| Action Item CIR-32.1 (MM 4.4.1e) | Update the County Zoning Code to include requirements and standards related to carpooling, bicycling, and transit amenities in development projects. | A $ | CDPD | Not yet programmed |
| Community Character Element |  |  |  |  |
| Action Item CC-3.1 | Examine the County’s sign ordinance and determine whether changes are needed to strike an appropriate balance between sign size and legibility. | C $ | CDPD | Revised ordinance adopted Oct. 2008 |
| Action item CC-10.1 | Undertake a regular review of the viewshed protection program to ensure its effectiveness and consider adding protections for views from Lake Berryessa to the program. | Ongoing $ | CDPD | Ongoing |
| Action Item CC-19.1 | In partnership with interested historic preservation organizations, seek funding to undertake a comprehensive inventory of the County’s significant cultural and historic resources using the highest standard of professional practices. | Ongoing $$$$ | CDPD Stakeholders | Not yet programmed |
| Action Item CC-19.2 | Consider amendments to the County zoning and building codes to improve the procedures and standards for property owner-initiated designation of County Landmarks, to provide for the preservation and appropriate rehabilitation of significant resources, and to incorporate incentives for historic preservation. | A $ | CDPD | Not yet programmed |
| Action Item CC-23.1 (MM 4.12.1) | In areas identified in the Baseline Data Report as having a significant potential for containing significant archaeological resources, require completion of an archival study and, if warranted by the archival study, a detailed on-site survey or other work as part of the environmental review process for discretionary projects. | Ongoing $ | CDPD | Ongoing implementation by staff during project review. |
| Action Item CC-23.2 (MM 4.12.1) | Impose the following conditions on all discretionary projects in areas which do not have a significant potential for containing archaeological or paleontological resources: • “The Planning Department shall be notified immediately if any prehistoric, archaeologic, or paleontologic artifact is uncovered during construction. All construction must stop and an archaeologist meeting the Secretary of the Interior’s Professional Qualifications Standards in prehistoric or historical archaeology shall be retained to evaluate the finds and recommend appropriate action.” • “All construction must stop if any human remains are uncovered, and the County Coroner must be notified according to Section 7050.5 of California’s Health and Safety Code. If the remains are determined to be Native American, the procedures outlined in CEQA Section 15064.5 (d) and (e) shall be followed.” | Ongoing $ | CDPD | Ongoing: implemented by staff during project review and included as a standard condition of approval. |
| Action Item CC-28.1 | Amend the Zoning Ordinance to provide a discretionary process such as a use permit by which owners may seek approval consistent with Policy CC-28 for an additional incentive for historic preservation. The process shall preclude reuse of buildings which have lost their historical integrity and prohibit new uses that are incompatible with the historic building or that require inappropriate new construction. | A $$$$ | CDPD | Planned for 2010-11 |
| Action Item CC-32.1 (MM 4.14.2b) | The County shall review and update as necessary its public works standards for street lighting to require the installation of fixtures which reduce the upward or sideways spillover of light consistent with the requirements of state law. | Ongoing $ | PW | Not yet programmed |
| Action Item CC-45.1 (MM 4.7.7) | The County shall use avigation easements, disclosure statements, and other appropriate measures to ensure that residents and businesses within any airport influence area are informed of the presence of the airport and its potential for creating current and future noise. | Ongoing $ | PW (Airport) CDPD | Ongoing: a requirement of adopted ALUC Compatibility Plans implemented by staff during project reviews |
| Action Item CC-53.1 | Work with the BAAQMD to disseminate information regarding regulations, monitoring, and enforcement for noxious odors. | Ongoing $ | PW CDPD DEM | Ongoing as needed |
| Conservation Element |  |  |  |  |
| Action Item CON-NR-1 | Amend the Conservation Regulations to offer incentives such as a streamlined review process for new vineyard development and other projects that incorporate environmentally sustainable practices that avoid or mitigate significant environmental impacts. | A $$$$ | CDPD | Not yet programmed |
| Action Item CON NR-2 (MM 4.6.1a) | The County shall seek grant funding and other support and establish a fisheries monitoring program(s) consistent with the efforts of the Watershed Information Center and Conservancy of Napa County in order to track the current condition of special-status fisheries and associated habitats in the County’s watersheds. Programs will include tracking the effectiveness of BMPs, mitigation measures and ongoing restoration efforts for individual projects in the watersheds and the implementation of corrective actions for identified water quality issues that are identified as adversely impacting fisheries. Monitoring programs shall be conducted in coordination with the State and Regional Water Boards, California Department of Fish and Game, U.S. Fish and Wildlife Service, and National Oceanic and Atmospheric Administration National Marine Fisheries Service to the extent necessary. | Ongoing $$$$ | CDPD WICC | The County acquired a grant to support program development. Fisheries monitoring needs will be identified as a part of the WAF grant, expected to be completed in 2010. Additional funding will be sought to implement monitoring. Limited fisheries monitoring is currently underway by RCD (JPA/contract). Year-long State grant funding freeze in 2009 has delayed program/schedule. |
| Action Item CON NR-3 (MM 4.6.5b) | The County shall amend its Local Procedures for Implementing CEQA to require gravel removal projects to result in no net adverse effects to stream temperature, bed attributes, or habitat necessary for native fisheries health. This may include restoration and improvement of impacted habitat areas (e.g., gravel areas and pools and woody debris areas). | B $ | CDPD | Not yet programmed |
| Action Item CON NR-4 (MM 4.6.5c) | The County shall adopt an ordinance that prohibits construction activities within the channel of any waterway identified to contain existing or potential spawning habitat for special-status fish species during limited time periods of spawning activities. | A $ | CDPD | Not yet programmed |
| Action Item CON NR-5 | The County shall maintain and update the Biological Resources and Fisheries chapters of the BDR as necessary to provide the most current data and mapping. Updates shall be provided online and made available for review at the Conservation, Development and Planning Department. The following specific data sets and maps shall be updated as needed: a) The County’s Biological Database (through the use of the California Department of Fish and Game’s California Natural Diversity Database (CNDDB) and information from the California Native Plant Society (CNPS)), including the addition of biological data to expand and improve the accuracy of the database and its usefulness to the public; b) Databases and mapping of sensitive biotic communities and habitats of limited distribution; c) Databases and mapping of oak woodlands and related sensitive biotic communities; d) Databases and mapping of riparian woodlands and related sensitive biotic communities; e) Databases and mapping of sloughs and tidal mudflats and related sensitive biotic communities. | As needed $ | CDPD | Ongoing updates: biological database is updated from updates received from CNDDB (Fish & Game) as well as from project bio-surveys. Databases and mapping of sensitive biotic communities and habitats of limited distribution and others (b-e) are based on the ICE Vegetation layer and are updated as the ICE veg-layer is updated, or periodically as new information becomes available. |
| Action Item CON NR-6 | The County shall adopt protocols to be followed, including a methodology for analyzing the need for buffers, and establish setbacks where discretionary projects are proposed on parcels that may contain sensitive biotic communities or habitats/communities of limited distribution or sensitive natural communities | A $$$$ | CDPD | The SWRCB and RWQCB are developing a methodology for stream-riparian/wetland buffers at this time. Protective buffers for discretionary projects are established via biological studies and consultant recommendations. |
| Action Item CON NR-7 | The County shall adopt a voluntary Oak Woodland Management Plan to identify and mitigate significant direct and indirect impacts to oak woodlands. Mitigation may be accomplished through a combination of the following measures: a) Conservation easement and land dedication for habitat preservation; b) Payment of in-lieu fees; c) Replacement planting of appropriate size, species, area, and ratio. | B $ | CDPD | A draft voluntary Oak Woodland Management Plan was completed. Currently out for public comment with adoption planned for 2010. |
| Action Item CON WR-1 | Develop basin-level watershed management plans for each of the three major watersheds in Napa County (Napa River, Putah Creek, and Suisun Creek). Support each basin-level plan with focused sub-basin (drainage-level) or evaluation area-level implementation strategies, specifically adapted and scaled to address identified water resource problems and restoration opportunities. Plan development and implementation shall utilize a flexible watershed approach to manage water resource quality and quantity. The watershed planning process should be an iterative, holistic, and collaborative approach, identifying specific drainage areas or watersheds, eliciting stakeholder involvement, and developing management actions supported by sound science that can be easily implemented. | B $$$ | CDPD | Efforts to initiate an IRWMP are currently underway by PW/Flood and CDPD. An integrated WS planning framework will be completed in 2010. Future development of WS management plans and IRWMPs for each of the major basins will be reliant upon State Prop 84 funding guidelines released in 2010. |
| Action Item CON WR-3 | Update the Conservation Regulations to establish an appropriate protective buffer (e.g., a special protection zone) in areas that drain toward any intake structure associated with the County’s sensitive domestic water supply drainages, requiring specific development and performance measures to protect water quality and balance property owners’ ability to use their land and stipulating that discretionary projects must be located outside of the protective buffer wherever this is feasible. | A $ | CDPD | Development of buffer options underway based on Federal/State recommended protections and local water purveyors input. Initial analysis completed and stakeholder outreach in-process. Public outreach and adoption planned for 2010-11. |
| Action Item CON WR-4 | Implement a countywide watershed monitoring program to assess the health of the County’s watersheds and track the effectiveness of management activities and related restoration efforts. Information from the monitoring program should be used to inform the development of basin-level watershed management plans as well as focused sub-basin (drainage-level) implementation strategies intended to address targeted water resource problems and facilitate restoration opportunities. Overtime, the monitoring data will be used to develop overall watershed health indicators, and as a basis of employing adaptive watershed management planning. | B $$$$ | CDPD WICC | Program development delayed in 2009 due to State funding freeze. Revised work program resumed in 2010 at reduced funding level and timeline. Program elements and data sources/gaps to be identified by June 2010. Limited fisheries monitoring currently underway as part of the RCD JPA. Additional habitat and WQ monitoring will be necessary in the coming years to comply with NPDES permit requirements. |
| Action Item CON WR-5 (MM 4.13.3.1a) | Identify, map, and disseminate information on groundwater recharge areas, to the extent feasible, and provide educational materials and resource information on ways of reducing and limiting the development of non-pervious surfaces in those areas. | A $$$$ | PW FCWCD CDPD | Grant funding for portions of this effort were frozen in 2009, but partial funding restored for 2010. Groundwater consultant has been retained and a study is underway. Study results expected June 2010. |
| Action Item CON WR-6 (MM 4.13.3.1a) | Establish and disseminate standards for well pump testing and reporting and include as a condition of discretionary projects that well owners provide to the County upon request information regarding the locations, depths, yields, drilling and well construction logs, soil data, water levels and general mineral quality of any new wells. | A $$$$ | DEM PW CDPD | Planned for 2010 completion as a part of CON WR-5 above |
| Action Item CON WR-7 | The County, in cooperation with local municipalities and districts, shall perform surface water and groundwater resources studies and analyses, and work towards the development and implementation of an integrated water resources management plan (IRWMP) that covers the entirety of Napa County and addresses local and state water resource goals, including the identification of surface water protection and restoration projects, establishment of countywide groundwater management objectives and programs for the purpose of meeting those objectives, funding and implementation. | B $$$ | CDPD PW DEM FCWCD | Develoment of an IRWMP framework is underway. Upon completion, local IRWMPs will be developed to align with larger regional efforts in the Bay Area and Sacramento River IRWMP Funding Areas (also see CON WR-1). Planned for 2010-11 completion. |
| Action Item CON WR-8 (MM 4.11.5a) | The County shall monitor groundwater and interrelated surface water resources, using County-owned monitoring wells and stream and precipitation gauges, data obtained from private property owners on a voluntary basis, data obtained via conditions of approval associated with discretionary projects, data from the State Department of Water Resources, other agencies and organizations. Monitoring data shall be used to determine baseline water quality conditions, track groundwater levels, and identify where problems may exist. Where there is a demonstrated need for additional management actions to address groundwater problems, the County shall work collaboratively with property owners and other stakeholders to prepare a plan for managing groundwater supplies pursuant to State Water Code Sections 10750-10755.4 or other applicable legal authorities. | Ongoing $$$$ | PW DEM CDPD | Grant funding for portions of this effort were frozen in 2009, but partial funding has been restored for 2010. A groundwater consultant has been retained and a study is underway. Study results are expected by June 2010. |
| Action Item CON WR-9 (MM 4.11.5c) | The County shall adopt a Water-Efficient Landscape Ordinance for multi-family residential, industrial, and commercial developments regarding the use of water-efficient landscaping consistent with AB 325. | A $ | CDPD PW | State Model (WELO) Ordinance became effective Jan. 1, 2010 and is currently being implemented. |
| Action Item CON WR-9.5 | The County shall work with the SWRCB, DWR, DPH, CalEPA, and applicable County and City agencies to seek and secure funding sources for the County to develop and expand its groundwater monitoring and assessment and undertake community-based planning efforts aimed at developing necessary management programs and enhancements. | Ongoing $ | CDPD CIA CEO | See CON WR-8 above. |
| Action Item CON CPSP-1 | The County shall develop a greenhouse gas (GHG) emissions inventory measuring baseline levels of GHGs emitted by County operations through the use of electricity, natural gas, fossil fuels in fleet vehicles and County staff commute trips, and establish reduction targets. | Ongoing $ | PW | County has developed its baseline inventory and action plan, which will be presented to the Board of Supervisors on March 16, 2010 |
| Action Item CON CPSP-2 (MM 4.8.7a) | The County shall conduct a GHG emission inventory analysis of all major emission sources in the County by the end of 2008 in a manner consistent with Assembly Bill 32, and then seek reductions such that emissions are equivalent to year 1990 levels by the year 2020. Development of a reduction plan shall include consideration of a “green building” ordinance and other mechanisms that are shown to be effective at reducing emissions. | 2008 $$$ | PW DEM CDPD | NCTPA completed a community-wide inventory/framework in 2009. A County Climate Action Plan to be completed in 2010. |
| Action Item CON CPSP-3 | The County shall conduct an audit within the next five years of County facilities to evaluate energy use, the effectiveness of water conservation measures, production of GHGs, use of recycled and renewable products and indoor air quality to develop recommendations for performance improvement or mitigation. The County shall update the audit periodically and review progress towards implementation of its recommendations. | A $ | PW | Periodic audits will follow the operational plan presented to the Board in March 2010 (See CON CPSP-1). |
| Action Item CON CPSP-4 | The County shall map Napa County’s biomass, wind, geothermal, solar photovoltaic, solar thermal, biofuel, landfill gas, and other potential renewable energy sources and partner with other organizations and industry to disseminate information about the potential for local energy generation. | B $ | PW CDPD DEM | Not yet programmed |
| Action Item CON CPSP-5 | The County shall quantify increases in locally generated energy between 2000 and 2010, and establish annual numeric targets for local production of “clean” (i.e., minimal GHG production) energy by renewable sources, including solar, wind, biofuels, waste, and geothermal. | 2010 $ | PW CDPD DEM | Planned for 2010 |
| Action Item CON CPSP-6 (MM 4.8.5) | The County shall periodically review and update the County Code to be consistent with requirements of CARB and the BAAQMD. | Ongoing $ | PW CDPD DEM | Planned for 2011-12 following CARB implementation of AB32 |
| Economic Development Element |  |  |  |  |
| Action Item E-13.1 | The County Board of Supervisors will be provided with periodic updates on the state of the County’s economy, in order to more effectively utilize County resources to promote countywide economic health. | Ongoing $$$$ | CEO WIB | Update to BOS planned for 2010 |
| Recreation and Open Space Element |  |  |  |  |
| Action Item ROS-1.1 | In cooperation with other public agencies and, in particular with the Napa County Regional Park and Open Space District, maintain a comprehensive inventory of public lands, including their existing and potential resource and recreational values. | Ongoing $ | RPOSD | Updated March 2009; Next update by June 2010 |
| Action Item ROS-1.2 | Modify the Zoning Ordinance as necessary to reflect the policies included in this Element and provide the appropriate level of review of proposed improvements and activities. | A $ | CDPD RPOSD | Zoning Ordinance amended in August 2009 (created Skyline Wilderness Park Combing District and amended Rural Recreation and Campground provisions) |
| Action Item ROS- 2.1 (MM 4.13.91b) | In partnership with the Napa County Regional Parks and Open Space District, establish numeric objectives for increased off-street trails and acreage of dedicated open space accessible to the public. | A $ | RPOSD PW CDPD | Numeric goals included in the RPOS District Master Plan adopted January 2009. Reevaluation planned in 2011 |
| Action Item ROS-2.2 | Support the Napa County Regional Park and Open Space District in developing, and updating at appropriate intervals, a new park and recreation master plan that identifies priorities, implementation strategies, and funding needs. | A $$$$ | RPOSD PW CDPD | RPOSD Master Plan for 2008-13 adopted January 2009. Review and update planned in 2011. |
| Action Item ROS-2.3 | Support sufficient and stable funding for the Napa County Regional Park and Open Space District. | Ongoing $$$ | RPOSD | District has requested BOS adopt 5 year policy on County funding; additional dedicated revenue source to be considered when the economy improves. |
| Action Item ROS-2.4 | Investigate and, where feasible, transfer the ownership and/or operation of existing County park facilities to the Napa County Regional Park and Open Space District. | Ongoing $ | PW RPOSD | Napa River Ecological Reserve management transferred to the RPOS District. Skyline Park transfer deferred until after it is possible to obtain fee title from the State. A fourth legislative attempt by County to acquire Skyline Park is underway; transfer of property to District subject to the outcome of this effort. No current plan to transfer Cuttings Wharf. |
| Action Item ROS-2.5 | Support the Napa County Regional Park and Open Space District in obtaining state, federal, and foundation grants, using methods such as preparing and adopting local plans and policies which may be required by various grant programs, and providing required local matching funds. | Ongoing $$$$ | RPOSD | NCRPOSD through Jan 2010 has obtained $3.8 M in non-county grants, $103,000 in volunteer support, and $45,900 in in-kind donations, matched by $1.6M in County grants. A draft voluntary Oak Woodland Management Plan is out for public comment, with adoption planned for 2010. |
| Safety Element |  |  |  |  |
| Action Item SAF-2.1 | Participate in local, regional, and state education programs regarding fire, flood, and geologic hazards. | B $ | CDPD PW FCWCD | An ongoing part of County and CDPD training programs. |
| Action Item SAF-8.1 | The County’s seismic fault maps shall be reviewed regularly to ensure that they reflect the latest information available. | B $ | CDPD PW | Map/database maintained as ongoing part of CDPD work program. |
| Action Item SAF-8.2 | Updated maps should be made available to the public at County offices, on the County’s Web site, and through other appropriate channels. | Ongoing $ | CDPD CalFire ITS EMS | Maps provided as an ongoing part of CDPD work program. |
| Action Item SAF-16.1 | Develop site criteria and construction standards for development in high fire hazard areas, and adopt standards to restrict urbanizing these areas as defined in Policy AG/LU-27 unless adequate fire services are provided. | Ongoing $ | CDPD CalFire | Building and Fire Codes periodically updated in compliance with state law |
| Action Item SAF-16.2 | Continue to implement “Napa Firewise” through information and education programs, community outreach, and fuel modification. | Ongoing $ | CalFire CDPD | Ongoing part of CDPD and CalFire work programs. |
| Action Item SAF-19.1 | The County will work with CalFire to develop improved methods of fire planning and firefighting for use in Napa County. | A $ | CalFire EMS | Ongoing part of CDPD and CalFire work programs. |
| Action Item SAF-31.1 (MM 4.9.2) | The County shall require written confirmation from applicable local, regional, state, and federal agencies that known contaminated sites have been deemed remediated to a level appropriate for land uses proposed prior to the County approving site development or provide an approved remediation plan that demonstrates how contamination will be remediated prior to site occupancy. This documentation will specify the extent of development allowed on the remediated site as well as any special conditions and/or restrictions on future land uses. | Ongoing $ | DEM PW CDPD | Required by CDPD and DEM as a regular part of their review of development applications |
| Action Item SAF-38.1 | Provide staffing and other resources as necessary to regularly update and implement the Napa Operational Area Hazard Mitigation Plan (NOAHMP). Consider new information regarding climate change and the expected severity and/or frequency of weather events in updates to the NOAHMP. | Ongoing $$$$ | EMS | NOAHMP was updated in 2009 and submitted to Cal EMA for approval (currently pending), and then forwarded to FEMA for final approval (expected 2010). |

Abbreviations

A= short term (1-5 years) 	BOS = Board of Supervisors					RPOSD=Reg. Parks & Open Space District		GIS=computerized mapping

B= longer term (5-10 years)	CDPD = Conservation, Development & Planning Department	PW =Public Works Department                                       GHG=green house gas

C=even longer term (10+ years)  	NCTPA =Napa County Transportation & Planning Agency	DEM =Department of Environmental Management

FCWCD=Flood Control & Water Conservation District	ITS=Information Technology Systems Department

CC= County Counsel     WIB= Workforce Investment Board	WICC=Watershed Information Ctr/Conservancy

CalFire=Calif Dept of Forestry & Fire Protections	CIA = Division of Community & Intergovernmental Affairs

$           - cost & level of effort is expected to be modest for the reasons stated

$$$$ - cost & level of effort will depend on policy direction & available resources

$$$       - cost & level of effort is expected to be substantial