October 2, 2006

Mr. Steven Lederer, Director

Upper Valley Agency

1195 Third Street, Room 101

Napa, California 94559

Subject: Contract Addendum Letter

Dear Steven:

HDR/Brown, Vence & Associates (HDR/BVA) is pleased to offer continued assistance to the Upper Valley Agency (UVA) for rate methodology services as related to Upper Valley Disposal Services (UVDS) and Clover Flat Landfill (CFL). As discussed, we have prepared a Scope of Work and associated Budget derived from our understanding of the work remaining to complete the project.

Scope of Work

Meet with UVDS/CFL – Tom Vence & Michael Greenberg will prepare and meet with all parties to discuss the current status of the rate methodology terms, including unresolved issues. Our proposed budget assumes one meeting.

Discussion/Analysis with UVA Staff – Work with staff to re-run analyses, conduct conference calls, and discuss and review new information. Our proposed meeting assumes 8 hours of discussion and analysis with staff.

Revise Report Letter – Revise current letter report to incorporate current status of issues.

Attend Board Meeting – Tom Vence & Michael Greenberg will prepare for and attend the October UVA Board meeting.

Prepare Rate Methodology – Prepare rate methodology to be used in revised contracts for UVDS and CFL. We assume all legal wording and review will be provided by UVA Counsel.

Attend Board Meeting – Tom Vence & Michael Greenberg will prepare for and attend one UVA Board meeting for approval of the new rate methodology contracts.

Budget

We propose to conduct the scope of work discussed above for a not to exceed amount of $16,908 including all labor and expenses. This amount will be treated as an addendum to the existing contract. A breakdown by work scope component is included below:

Meet with UVDS/CFL – $1,478 (7 hrs)

Discussion/Analysis with UVA Staff – $1,585 (8 hrs)

Revise Report Letter – $793 (4 hrs)

Attend Board Meeting – $1,616 (7 hrs)

Prepare Rate Methodology – $9,028 (48 hrs)

Attend Board Meeting – $2,408 (11 hrs)

Due to the uncertainty in the response(s) from UVDS/CFL and the associated required actions, UVA may want to allocate a contingency of 25% to cover these potential unplanned events. The contingency would only be accessed upon authorization by the UVA Director. A 25% contingency would add $4,227 for a total of $21,135.

We appreciate the opportunity to continue working with you on this exciting project. Please contact me at (415) 434-0900 x125. Thank you.

Very truly yours, 
HDR/BROWN, VENCE & ASSOCIATES

Michael Greenberg

Michael G. Greenberg, P.E.

Vice President

Cc: Tom Vence, Vence Consulting