## Appropriation Request
DEVLIN ROAD SEGMENT E PROJECT | NOVEMBER 5,2018
PROJECT, RDS 11-06
DESIGN PHASE
|  | Board Appropriation | Board Appropriation | Appropriation Amount | Appropriation Amount | Appropriation Amount
Budget Item | Budget Item Amount | Request Today | to date | Spent to Date | % Spent to Date | Balance
Construction | 3500000 | 50000 | 0 | 0 | 0% | 0
Construction Contingency (15%) | 525000 | 0 | 0 | 0 | 0% | 0
Design and Engineering: | 840000 | 50000 | 747087 | 697778.08 | 93.4% | 49308.92
Chaudhary and Associates - $100,000 | [6 empty] | Is Construction Admin in this?
Monk and Associates - $30,000
Rincon Consultants - $10,000 | [6 empty] | 0
Design and Engineering Contingency | 84000 | 0 | 0 | 0 | 0% | 0
Lands and Temporary Construction Easement | 635000 | 40000 | 595000 | 593073 | 99.68% | 1927
Construction Management and Construction Administration | 450000 | 50000 | 0 | 0 | 0% | 0
County Project Management/Administration | 430000 | 15000 | 300000 | 277883.69 | 92.63% | 22116.31
Special Inspections and Fees | 50000 | 5000 | 10000 | 7760.96 | 77.61% | 2239.04
CM/CA/INSP Contingency | 0 | 0 | 0 | 0 | 0% | 0
Permits/ Post construction monitoring/reporting | 36000 | 0 | 0 | 0 | 0% | 0
TOTAL | 6550000 | 210000 | 1652087 | 1576495.73 |  | 75591.27
Note on B8: Wadsworth, Graham: From 95% cost estimate by Chaudhary & Associates and AECOM
Note on C8: Wadsworth, Graham: Estimate for tree removal
Note on B13: Wadsworth, Graham: Amendment 2 for design and estimate for construction support