Milestones, Project Tasks and Budget

Watershed Assessment Framework (WAF):  North-Bay and Delta Scoping and Napa River Pilot Project

A coordinated effort to develop performance measures and indicators for “watershed health” as a means of evaluating and reporting on ecosystem services and socio-economic benefits/conditions in the Napa River watershed and across the North Bay-Delta region. The Napa River watershed will serve as the pilot watershed and will be the focus of the data analysis phase of the project.

| Project Milestones | Due Date |
| --- | --- |
| Stakeholder involvement & education and refinement of watershed goals | Ongoing, Goals by January 2009 |
| Linking of goals to watershed indicators to inform attributes of the WAF, finalization of indicator plan | June 2009 |
| Scientific analysis of indicators & aggregation into multi-metric watershed indices | October 2009 |
| Investigation of theoretical issues associated with indicator/index system | October 2009 |
| Development of a preliminary, easily-understood & communicated “score-card” method | January 2009 |
| Stakeholder communication in other watersheds within North Bay-Delta to gain feedback on applicability on approach & findings | Ongoing, Through March 2010 |
| Reporting of findings on application of the WAF at a focused/pilot level & potential application across the North Bay-Delta region | March 2010 |
| Coordination with nearby WAF projects (SFEI/SFEP/SRWP & others) & participation in proposed Statewide Coordination Council | Ongoing, Through June 2010 |
| Technical report & executive summary to CALFED/DWR & other stakeholders on approach, lessons learned, & applicability of findings to North Bay-Delta region | June 2010 |

| Project Work Task | Task Description | Contributing Partner’s In-kind Match | Grant Funds Awarded | Project Total |
| --- | --- | --- | --- | --- |
| Task 1: Develop basis for assessing watershed conditions | Develop knowledge base of possible analytical approaches, potentially available data, and reporting strategies to present to Local TAC & State Coordinating Council | $30,000 | $49,000 | $79,000 |
| Task 2: Local and regional coordination | Convene and meet with stakeholders and advisory committees, communicate and receive feedback on watershed goals, analysis approach and reporting needs | $18,410 | $37,000 | $55,410 |
| Task 3: Develop indicator analysis and reporting plan | Develop regional indicator framework, plan for analysis in focus/pilot watershed and preliminary reporting/"score card" method (w/State Coordinating Council) | $13,000 | $41,500 | $54,500 |
| Task 4: WAF indicator analysis in focus watershed | Analyze indicators and indices corresponding to all 7 WAF attributes, describe process, findings, interpretation and limitations | $22,000 | $183,000 | $205,000 |
| Task 5: Report findings for watershed and WAF testing | Report regional framework of indicators, report analysis of WAF indicators for Napa River watershed, description of stakeholder and scientific analysis process, and reporting of lessons learned, gaps, etc. in cooperation with Coordinating Council | $7,000 | $50,000 | $57,000 |
| Administration: |  | Included in rates above |
| Reporting: |  |  | $22,500 | $22,500 |
| Invoicing: |  |  | $11,000 | $11,000 |
|  |  | $90,410 | $394,000 | $484,410 |