Napa County General Plan Update

Preliminary Schedule

| Task | Time Frame |
| --- | --- |
| Task A: Project Start-up |
|  | 1. County Project Initiation | July 2004 |
|  | 2. Refine Scope | July - October |
|  | 3. Select Advisory Committee(s) | November - January |
|  | 4. Consultant Selection Process | December – January |
|  | 5. Kickoff Update Process | January - February 2005 |
| Task B: Background Data Collection |
|  | 1. Baseline Data Report Completed | January – March 2005 |
|  | 2. Existing Conditions Public Workshop | March – April 2005 |
| Task C: Vision and Key Issues |  |
|  | 1. Identify Issues | April - July 2005 |
|  | 2. Public Workshop: Vision and Issues | May 2005 |
|  | 3. Develop Vision Statement | August - September 2005 |
| Task D: Alternatives Development, Analysis and Selection |
|  | 1. Formulate Alternatives | October - December 2005 |
|  | 2. Public Workshop: Develop Alternatives | November 2005 |
|  | 3. Conduct Alternatives Analysis/Evaluation | December 05 - February 06 |
|  | 4. Public Workshops: Review/Select Alternatives | February 2006 |
|  | 5. Select/Refine Preferred Alternative | March 2006 |
|  | 6. Finalize Language of Ballot Measure(s) | May – August 2006 |
| Task E: Draft General Plan |
|  | 1. Draft Goals and Policies | April - June 2006 |
|  | 2. Administrative Draft General Plan | July – September 2006 |
|  | 3. Draft General Plan | October 2006 |
|  | 4. Measure J Election | November 2006 |
| Task F: Draft EIR |
|  | 1. Notice of Preparation | June 2006 |
|  | 2. Prepare Administrative Draft EIR | August – September 2006 |
|  | 3. Draft EIR | October 2006 |
| Task G: Revision and Adoption |
|  | 1. Review and Revise General Plan | November 2006-March 2007 |
|  | 2. Final General Plan and EIR | April 2007 |
|  | 3. Adopt General Plan | June 2007 |

* Steering Committee will meet as needed from January 2005 – September 2006

** Public Workshops shown are preliminarily suggested – actual number of meetings and schedule may vary