## Roads
2005/2006 Flood Repair Projects to be Completed - Status 01/29/08
|  | FEMA/OES | Actual | Spent | Status | Project
Project | PW # | Funded Amount | Budget | to | Geotech | Completion
|  |  | Estimate | Date | (completion | Deadline
Roads: |  |  |  |  | date)
5 Eligible Projects - Scheduled for Construction 2008
Diamond Mountain Road | 856 | 48186 | 400000 | 41028.89 | COMPLETED | 2008-12-05
4700 Block Redwood Road | 2758 | 347012 | 1000000 | 57327.66 | COMPLETED | 2008-10-14
Spring Mountain Road | 3538 | 201611.69 | 350313.69 | 37374.22 | COMPLETED | 2008-10-14
Steele Canyon MPM 2.00 | 2891 | 345347.56 | 1068000 | 71615.28 | COMPLETED | 2008-10-14
Steele Canyon MPM 2.25 | 3227 | 89463.69 | 312000 | 55938.46 | COMPLETED | 2008-10-14
Subtotal |  | 1031620.94 | 3130313.69 | 263284.51
1 Eligible Project - Scheduled for construction 2009
4800 Block Redwood Road (Site 1)*** | 2890 | 296658.11 | 1000000 | 39762.14 | COMPLETED | 2009-10-14
4800 Block Redwood Road (Site 2)*** | 694 | 59252.86 | 700000 | 0 | COMPLETED | 2009-10-14
Subtotal |  | 355910.97 | 1700000 | 39762.14
Total - Eligible Projects |  | 1387531.91 | 4830313.69 | 303046.65
3 Non-eligible Projects - Scheduled for construction 2009
Dry Creek Road | 311 | 0 | 600000 | 0 | Envmtal
Whitehall Road | 3546 | 0 | 350000 | 10932.15 | Geo-tech
White Sulphur Springs Rd. | TBD | 0 | 800000 | 2898.77 | Scope
Total - Non-Eligible Projects |  | 0 | 1750000 | 13830.92
Grand Total Eligible & Non-Eligible |  | 1387531.91 | 6580313.69 | 316877.57
Projects
*** 4800 Block Redwood Road Road (Sites 1 and 2) are considered as one eligible location for construction purposes