## Cost Estimate
TABLE 1
Cost Estimate For Upgrades/Modifications to the Leachate Distribution System
American Canyon Landfill
|  |  | Task 1 -Conceptual Design and Work Plan |  | Task 2 - Preliminary Design / Plan |  | Task 3 - Final Design / Plan |  | Task 4 - Engineering Support During Construction / Startup |  | Total
Cost Code |  |  | 01010000 |  | 01020000 |  | 01040000 |  | 01040000
Labor |  | Rates | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Dollars
Staff Engineer |  | 75 |  | 0 | 20 | 1500 | 8 | 600 |  | 0 | 28 | 2100
Design Engineer, Tony Gokoffsiki |  | 139 | 20 | 2780 | 20 | 2780 | 40 | 5560 | 40 | 5560 | 120 | 16680
Field / Construction Engr, Ken Brown |  | 95 | 8 | 760 | 8 | 760 | 8 | 760 | 16 | 1520 | 40 | 3800
Project Manager, J. C. Isham |  | 140 | 12 | 1680 | 8 | 1120 | 8 | 1120 | 8 | 1120 | 36 | 5040
Landfill Gas Engineer Andy Wang |  | 110 | 4 | 440 | 4 | 440 | 8 | 880 |  |  | 16 | 1760
Drafting |  | 76 | 8 | 608 | 16 | 1216 | 8 | 608 | 4 | 304 | 36 | 2736
Clerical |  | 40 | 4 | 160 | 4 | 160 | 4 | 160 | 4 | 160 | 16 | 640
Subtotal Labor |  |  |  | 6428 |  | 7976 |  | 9688 |  | 8664 |  | 32756 | 32756
Expenses
Transportation |  |  |  | 100 | [5 empty] | 200 |  | 300
H&S Monitoring and Field Equipment | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 50 |  | 50
Consumables and Supplies | 0 | 0 |  |  | 0 |  |  |  |  | 50 |  | 50
|  |  |  | 100 |  | 0 |  | 0 |  | 300 |  | 400 | 400
Subcontractors/Suppliers
|  |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 0 |  | 0
Subtotal Subcontractors | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Grand Totals |  |  |  | 6528 |  | 7976 |  | 9688 |  | 8964 |  | 33156 | 33156
Assumptions: